## Slide 1
LNA Nova: Prompt Builder Re-Engineering
Why Re-Engineer Now
LNA Nova generates outreach emails across 4 topics. Today, only 1 of 4 uses Salesforce Prompt Builder — the other three embed ~8,000 words of generation logic directly in topic instructions, forcing the AI planner to orchestrate AND compose simultaneously.
Issue | Risk | Example
Inconsistent output quality | Planner-generated emails drift in tone, structure, compliance | Nudge emails include sign-offs, vary in length, miss reframe
Spelling locked to UK English | Cannot serve US market leads with US conventions | Every email says "organisation" regardless of country
Fragile record updates | Planner must recall exact picklist values | "Customer Not Interested" vs "Not Interested" → automation failures
High maintenance cost | Editing XML topic instructions requires full redeployment | No version control, no A/B testing, no prompt iteration
Cannot scale | New locale/industry = rewrite topic instructions | No modular pattern to extend
THE ASK
Approve the re-engineering effort to migrate all four topics to the Prompt Builder framework with locale-aware spelling (UK + US English), establishing a scalable pattern for future agent expansion.
Statista · FDE · Agentforce SDR · Confidential

## Slide 2
Target Architecture
Design: Topic → Flow → Prompt Template
TOPIC
Scope & Guardrails
2 instructions: • What to do • Guardrails Planner decides WHEN, not HOW
FLOW
Orchestration & Updates
1. Get Lead (+Country) 2. Resolve Locale 3. Call Prompt Template 4. Update records 5. Return email
PROMPT TEMPLATE
Generation & Personalisation
Full generation logic with dynamic SpellingLocale input LLM decides HOW
▶
▶
Locale Resolution (New Capability)
Lead.Country → Flow Decision → SpellingLocale ("UK" or "US") → Prompt Template
• Deterministic — Flow-side decision, not LLM judgment
• Extensible — Add Australian English by adding one Decision branch
• Safe default — UK English for all non-US countries (matches current production)
• US mapping — "United States", "USA", "US", "U.S.", "U.S.A.", Puerto Rico, Guam, territories
Statista · FDE · Agentforce SDR · Confidential

## Slide 3
What Changes
Component | Current State | Re-Engineered State
Topic Instructions | 21 instructions (~8,000 words in XML) | 8 instructions (~800 words — scope + guardrails)
Prompt Builder Templates | 2 (Persona Detection + Outreach Email) | 5 (+Follow-Up Nudge, Meeting Response, Opt-Out)
Orchestration Flows | 2 (Initial Outreach + Update Lead) | 5 (+Follow-Up Nudge, Meeting Response, Opt-Out)
Record Update Logic | Mixed — 2 in Flows, 2 rely on planner | 100% in Flows — all values hardcoded declaratively
Planner Steps per Topic | 3-5 (action calls + composition) | 1 (invoke flow)
Spelling Locales | 1 (UK only, hardcoded) | 2 (UK + US, dynamic per Lead.Country)
Country in Flow Queries | 0 of 2 flows | 4 of 5 flows (all customer-facing)
New Deliverables
# | Deliverable | Type | Scope
1 | LNA_Nova_Follow_Up_Nudge | Prompt Template + Flow | Migrate 6 topic instructions → 1 PT
2 | LNA_Nova_Meeting_Response | Prompt Template + Flow | Migrate 7 topic instructions → 1 PT
3 | LNA_Nova_Opt_Out_Response | PT + Flow + branching | Migrate 6 instructions → 1 PT + classification
4 | Locale Resolution Layer | Flow Decision (x4) | Country → SpellingLocale mapping
5 | Outreach Email + Initial Flow updates | PT + Flow modification | Add SpellingLocale input + Country query
6 | All 4 topic updates | PlannerBundle mod | Reduce instructions, swap actions
7 | US English test suite | Test data | Clone UK tests with Country = "United States"
Statista · FDE · Agentforce SDR · Confidential

## Slide 4
Delivery Plan & Estimates
Phased rollout — each phase independently deployable
Phase 0
Locale Foundation
Update existing flow + PT for locale support
~2 days
LOW RISK
Phase 1
Follow-Up Outreach
New PT + Flow Update topic No record updates
~3 days
LOW RISK
Phase 2
Meeting Response
New PT + Flow Update topic 1 record update
~3 days
MEDIUM RISK
Phase 3
Opt-Out Response
New PT + Flow 3-way classification Compliance fields
~4 days
HIGHEST RISK
Phase 4
Cleanup & Deployment
US test suite package.xml Full regression
~2 days
LOW RISK
Total Estimate: ~14 days | 5 phases | Each phase independently deployable | Zero downtime between phases
Key Dependencies
• Salesforce org access for scratch org testing • Knowledge articles must remain published • Country field values validated against locale mapping
Statista · FDE · Agentforce SDR · Confidential

## Slide 5
Return on Investment & Scale Readiness
Immediate Returns
Benefit | Metric | Impact
US market readiness | Locales: 1 → 2 | US lead outreach without manual editing
Output consistency | Planner steps: 3-5 → 1 | Same structure every invocation
Record reliability | LLM field deps: 3 → 0 | Zero picklist value errors
Iteration speed | Edit PT → publish | No agent bundle redeployment
Maintenance | 8,000 → 800 words | 90% less prompt logic to maintain
Future Scale: What This Enables
Scenario | What to Build
New locale (e.g., AU English) | 1 Decision branch per Flow
New industry | 1 ICP Knowledge article + Flow branch
New cadence stage | 1 Topic + 1 Flow + 1 PT
New agent (e.g., CS Rep) | Clone pattern, swap prompts
A/B testing variants | PT version management in UI
Model swap (Gemini → Claude) | Change primaryModel in PT metadata
Architecture Maturity
CURRENT
• Monolithic (8K words in topics)
• Fragile (planner composes emails)
• UK-only (hardcoded spelling)
• 1 of 4 topics uses Prompt Builder
RE-ENGINEERED
• Modular (800 words — scope only)
• Deterministic (Flow orchestration)
• Locale-aware (UK + US dynamic)
• 4 of 4 topics use Prompt Builder
▶
Recommendation: Approve the 14-day effort across 5 phases. Pays for itself immediately via US market enablement; compounds as each new locale, industry, or agent reuses the pattern.
Statista · FDE · Agentforce SDR · Confidential